|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **Indenture level** | **Element Title** | **Duration (in days)** | **Reason** | **Resources** |
| 2 | Concept Review | 5 | Will allow the project manager to review the project planning thoroughly. | Andy Johns |
| 1 | Safety and Environment | 15 | The subtasks of this task will be parallel. | Kabelo Mohapi, Neo Mohapi |
| 2 | Safety Analysis Report | 15 | Allows the discussion of hypothetical accident and propose safety measurement that will prevent such accident. |  |
| 2 | Probabilistic Risk Assessment | 15 | Will allow notification and examination of events that put the project in abnormality. | Neo Mohapi |
| 1 | Preconstruction | 39 | Enough to confirm quality before construction. |  |
| 2 | Waste Acceptance Criteria | 15 | The duration will allow well application of remediation activities that will production to comply with latest environmental standards. | Project Support Officer |
| 2 | Quality Assurance | 10 | The duration is enough to allow measurement of correctness, efficiency, maintainability of the designs before implementation takes place. | Andy Johns |
| 2 | Subcontractor Training | 30 | Will allow proper training subcontractors so that they meet specific requirements. | Blantina Morake |
| 2 | Readiness Review | 7 | The time will allow Andy to ensure that all administrative and physical control are obtained and set up before construction commence and to review quality again. | Andy Johns |
| 2 | Site-clearing permission | 3 | It does not take longer to get response from municipality. | Andy Johns |
| 2 | Communication Strategy | 5 | Enough to pass the message of how communication will be conducted. | Emelia Mohapi |
| 2 | Support Services | 40 | Will allow support service to be conducted through design to assist stakeholders with problems related to work and social life. | Project Support Officer |
| 2 | Complete Production Train Inspection | 5 | Will allow full inspection of the train shop before final approval commence. | Andy Johns |
| 2 | Paint Shop Inspection | 5 | Will allow full inspection of the paint shop before final approval commence. | Andy Johns |
| 2 | Building Inspection | 4 | Will allow proper inspection of the building before final approval commence. | Andy Johns |
| 2 | Final Approval | 3 | Since the inspection were performed final approval be conducted quickly with results already known. | Local Inspection Authority |
| 3 | Foundation | 10 | The building is just expanded, two is enough. | Daniel Lee |
| 3 | Structures | 10 | The building is just expanded, two is enough. | Derek Rivett |
| 3 | Roofing | 10 | The building is just expanded, two is enough. | Justine Leakey |
| 3 | Water Proofing | 10 | The building is just expanded, two is enough. | Manzi Nisela |
| 3 | Building Electrification | 10 | The building is just expanded, two is enough. | Ollie Volta |