## Sheet1
DVP PROJECT - RISK REGISTER |  | Version | 1 |  |  | Date | 2001-11-03
Risk | Causes (due to …) | Probability | Impact | Risk Rating | Response | Actions | Start | End | Responsible
Date for completing the project after 1 January 2002 | Type Approval taking longer than 4 weeks as quoted | H | H | H | Mitigate | Meet with Alcatel and CSAA to discuss the issues and resolve | 2001-11-03 | asap | Zhou Jianglin
| Fujitsu equipment taking longer to engineer than estimated and "go live' pushed back to 5 Feb 2002 to remain cost neutral | H | H | H | Mitigate | Set up meeting with all technology stakeholders (JBC, Nortel, Alcatel, Fujitsu) to discuss technical issues for the integration of equipment, and timelines | 2001-11-03 | asap | Zhou Jianglin
Amount by which the project budget of RMB 110 million is exceeded | Routine maintenance and monitoring for 12 weeks had to be included in the training of new hires | M | M | M | Mitigate | Establish relevant parties involved in hiring and training. Establish scope of training. Who will do hiring and who will do training. What will the timelines and costs be? | 2001-11-03 | 2001-12-01 | Zhou Jianglin
| CSAA testing fee increased from RMB 30000 to RMB 150000 and Alcatel refuses to pay | H | M | H/M | Mitigate | Meet with Alcatel and CSAA to discuss the issues and resolve. Agree on cost and payment. Report back to MD. | 2001-11-03 | asap | Zhou Jianglin
Complexity of delivering the new "scaled-down" specification | Inclusion of Alcatel new VIT voice equipment, Fujitsu current voice equipment, centrally-controlled network | H | H | M | Mitigate | Set up meeting with all technology stakeholders (JBC, Nortel, Alcatel, Fujitsu) to discuss technical issues for the integration of equipment, and timelines | 2001-11-03 | asap | Zhou Jianglin
Technology does not meet customer expectations | Only half the original coverage of date and voice lines will be delivered | M | M | M | Mitigate | Engage with Marketing function of the company look at a campaign to manage customer expectations and potential reputational impacts on the company | 2001-11-03 | 2001-12-01 | Zhou Jianglin and Marketing
| Quality of service compromised - network outages 3% of time | M | M | M | Mitigate
Network Maintenance not done to the right quality level | New hires to be trained - no experience in maintenance | M | M | M | Mitigate | Ensure the training is thorough and includes experiential aspects | 2001-11-03 | 2001-12-01 | Zhou Jianglin and Training Manager
Insufficient experienced PM staff on project | Zhou not a trained PM. Hiring of trained PM and extra staff refused | M | M | M | Mitigate | Engage with experience PM as a mentor - Paul Scott | 2001-11-03 | ongoing | Zhou Jianglin
Complexity of Stakeholder management | More vendors (Alcatel and Fujitsu) | M | M | M | Mitigate | Set up regular stakeholder meetings to discuss project progress and issues | 2001-11-03 | asap | Zhou Jianglin